GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH

Ministry of Finance/Internal Resources Division

National Board of Revenue

(NBR)

Term of References (TOR)

FOR

Selection of National Consulting Firm

For

Package SD15.3

Taxpayer Awareness Building Campaign-TV Advertisement, Clipping etc

# Service Type: TVC Making, Broadcasting, Media Planning

Beneficiary Country: Peoples Republic of Bangladesh

Contracting Authority: Vat Online Project (VOP), The National Board of Revenue (NBR)

- Background of the Project

The National Board of Revenue (NBR) has been allocated public funds from the Government of the People’s Republic of Bangladesh (GOB) (which has been provided funds to support this project through the World Bank’s Program for Results) towards the cost of “VAT and Supplementary Duty Act, 2012 (online) Implementation Project” and, intends to apply part of the proceeds with these funds for eligible payments to selected firms/agencies for delivering the services as per scope of the project.

To properly implement and effectively administer the new VAT law, the NBR, initiated its VAT Online Project (VOP). This new system will provide the best fit for the organization’s new business practices and processes. The VOP has been tasked with introducing a modern, user friendly and efficient VAT program through consultation, collaboration and co-design of the system.  The National Board of Revenue (NBR) has established Project Implementation Unit (PIU) under the Vat Online Project (VOP). The activities of the PIU will contribute towards increasing access to new VAT services and improve VAT law in Bangladesh. In order to reach these objectives, a nationwide inter-active multi-media campaign will be launched using audio, video, print and online media.  Against this backdrop, the NBR is seeking to appoint an eligible firm/agency to produce and disseminate television commercial (TVCs) materials for increasing awareness among national taxpayers.

- Objectives of the assignment:

Key objectives of the NBR’s taxpayer awareness program are expected to influence, educate, change and enthuse taxpayers to comply with the new VAT law.  The awareness program is also expected to underpin the correction process for those who will not comply with the new law.

It should be noted that the success of this awareness and outreach program would be depended upon achieving the following specific communication sub-objectives, which the interested vendor must address in their production:

- Information dissemination about VAT, new VAT Law and VAT online project among public and the tax payers.

- Building trust between taxpayers and the Government by underlining transparency, positive and effective sides of the new VAT system.

- Constructing positive attitudes of the VAT Payers, VAT collectors and general public towards VAT.

2.a. Message Framing

Messages of these campaign products are required to be framed around four key themes that compliments above specific communication sub-objectives:

- Information and Education: Information and education refers to the dissemination and education of members of public including tax payers regarding what is VAT, the new online VAT system, new payment and accounting system, how the new law is different than the old law, how to register, who needs to be registered and why it is important to register.

- Encouragement and Awareness: Refers to encourage and aware VAT payers to register online, and enthuse them to adopt the new system.

- Advocacy and Influence: Here refers to turning VAT payers as advocates of the new law who would also influence peers towards welcoming the VAT online system. In this regard it is important that documentary productions would highlight the fact that the VAT payers and end consumers are contributing in building Bangladesh.

- Correction: Here refers to the implication for not complying with the law.

2.b.1 Primary Audience

- The Primary audience of this campaign is general public including the VAT payers (businessmen/ shop owners/corporations).

- Young generation.

- Influencer (including civil society members, celebrities and academia)

- Media as a multiplier

2.b.2 Secondary Audience

- NBR officials working across the country.

- Other Government agencies would be aware of this initiative.

3. The Scope of Services (Including Production and Dissemination):

3.a.1. TVCs Production: Six TVCs with a general length between 40 seconds to a 100 seconds should be produced and disseminated with an aim to meet three objectives and Four-message framing approaches mentioned above.

3.a.2. Type of Advertisement: During the broadcast of these TVCs, the TV screens must broadcast selected TV scrolls (at least four in total) on VAT and the TV screens must be branded by the VAT online logo for few seconds. Length of logo branding during the broadcast of the program would be subject to agreement between the PIU and the service provider. News Tag line, Pick hour News Name etc.

3.a.3 Broadcast Schedule: Spread over about 500 days intermittently in leading private and government TV channels where indicative spot/insertion should be at least 8000. The interested agency/firm must provide a detail media plan. That particular media plan must include a media buying schedule including names of television channels where these sport assertions would take place and times of broadcast featuring peak, super peak and off peak times. This media plan should use latest TRP rating as a basis of selecting TV channels for the dissemination of the campaign products- here by refers to TVCs. The broadcast schedule and media plan must get approval from the PIU.

3.a.4. Broadcasting time for Lottery Schedule and media coverage: Yearly 4 lottery competition and some loyalty programme will be arrange. 1 hour live programme will broadcast in different 4 channels in a year. And each partnership MOU should have some media coverage in TV Scroll, News, Business Reports etc.

(Proprietary Rights of all final production materials will be retained by the NBR)

N:B: Service provider give the plan with a proper FGD and market analysis.

3.b. Table 1. Indicative Required Key Professionals:

| Designation | Qualification | Experience |
| --- | --- | --- |
| Director for TVC production (1X6 person months spread over the contract period) | University degree (Minimum Bachelor’s degree) | - Minimum 5-7 years of experience in directing and managing TVC productions - Previous experience of working with the government would be a plus. |
| Production manager (1X 6 Person months spread over the contract period) | University degree (Minimum Bachelor’s degree) | - At least five years of experience in relation to production and management. |
| Cameramen (2X 3 person months) | University Education (Minimum Bachelor’s degree) | - Experiences in multidimensional video production. |
| Creative Writer (1X2 person months spread over the contract period) | University Degree (Minimum Bachelor’s Degree) | - At least three years in relation to creative writing for TVCs. |
| Content Developer (1X2 person months spread over 30 months) | University Degree (Masters Degree) | - Should have minimum 20 years of working experience in Customs, Excise and VAT Department - Proven experience on producing content for tax- payer communication materials. - Should have proven writing-experience on tax matters to the taxpayers - Should have proven excellent capability of legal translation from Bangla to English and vice versa |

- b. Table 2. Required Indicative Other Professionals

| Editor and Mixer (1X6 person months spread over 30 months) | University degree (Bachelor’s Degree) | - At least five years of experience in editing and mixing video productions for documentary |
| --- | --- | --- |
| Talent manager (1X3 person months spread over 30 months) | University degree (Minimum Bachelor’s degree) | - At least five years experience in talent management |
| Media Planner (1x6 months spread over 30 months | University Degree (Minimum Bachelor’s Degree) | - At least five years media planning experience; - Excellent connection with journalist and TV Channels - Excellent knowledge about TV Programmes |
| Client Service (1X6 months spread over 30 months | University Degree (Minimum Bachelor’s Degree) | - Excellent Good in English and Bangla; - Five years experience in agency client service; - Vast Idea about media planning; - Very good in communication (Phone, Email, Facebook, Msg any messenger); - Understand the tuning of clients requirement; |

4. Period of Performance

Expected contract period is September 2016 to December 2018.

4.a. Deliverables:

Six TVCs, TV scrolls in appropriate media format alongside of following detailed reports comprising when and where those media products and scrolls were broadcasted.  Indicative detail contents of each report are written below.

| SL No | Milestone & Deliverables | Content & Number of Copies | Schedule |
| --- | --- | --- | --- |
| 1 | Inception Report- Work Plan | 1 Paper and 4 electronic Copies | Within 30 days of the inception of the work |
| 2 | Quarterly Progress Report | 1 Paper and 4 electronic Copies | In every four months from the inception of the work (at least three). |
| 3 | Completion Report (all requested deliverable ) of the Taxpayer Advertising Campaign | 1 Paper and 4 electronic Copies | Within a month of the completion of the project |
| 4 | Indicative TRP report | 1 Paper and 4 electronic copies | Within a month of the completion of the project |
| 5 | Contents of media products in DVDs and USBs | 10 copies | With completion report (10) |

- The consulting firm/agency will prepare contents of the aforementioned broadcast materials and prepare dissemination of these materials after obtaining the approval of the relevant NBR authority.

- All contents produced for this project needs to be delivered in MP4 and AVI format in pen drives and DVDs.

- The consulting firm should prepare reports (see the schedule of reports below), describing plan, progress and completion of the assignment. These reports should provide a clear presentation and include a table of contents and an executive summary.

- All paragraphs in the executive summary, the text, and the Annexure, shall be numbered to facilitate communication on the contents of reports.

- All reports shall be accompanied with a PDF soft copy on a CD (1 Master and 3 additional copies shall be included)

4.b. Content of Reports

Following reports are required to submit to PIU, Dhaka:

- Inception Report – Work Plan (Draft and Final):

Within the ten days of selection of the contract, the consulting firms must provide a draft inception report which will include a detailed work plan which shall contain the final detailed time-task-schedule charts listing all the tasks, estimate by task of both the staff time input by the consulting firms and counterpart personnel and the time requirement for task completion in bar chart format and also include supporting text describing the bases for the program.  The PIU, NBR will make all efforts to furnish comments on the Inception Report -Work Plan within a week of the reception of the draft inception plan.

- Quarterly Progress Report

Quarterly Progress Report must include, among others, content of the report, photographs of each activity completed in each quarter and a list of media content under production/ are produced. If those contents are disseminated through media outlets, the report must ensure it features a list of outlets through which those media contents were disseminated including the time of the dissemination. Soft copies of finished products in the case of completion of production at the time of the submission of respective quarterly progress reports must be accompanied with the report.  The total number of quarterly progress report must be at least three but depending upon the campaign roll out plan, procedure and implementation, the number of progress report delivery could be enhanced to 4. If the PIU advised so four quarterly progress report, the firm/agency must comply with that demand.

| Name of the Content | Progress Report | Time Schedule |
| --- | --- | --- |
| 1: TVC Production 2 Draft Copy | By DVD | 1st Quarter |
| 2. Broadcasting Plan | By A4 size in Xcel Sheet by Dropbox |  |
| 3. Broadcasting plan for media coverage and lottery |  |  |
| 1: TVC Production 2 Final Copy | By DVD | 2nd Quarter |
| 2: TVC Production new 2 Draft Copy | By DVD |  |
| 3: Broadcasting/Telecasting Plan | By A4 size in Xcel Sheet by Dropbox |  |
| 4: Lottery and Loyalty Program Media Coverage plan | By A4 size in Xcel sheet and drop box |  |
| 5: Media Monitoring report with viewers reaction | By A4 Size Page in Xcel Sheet in drop box |  |
| 1: TVC Production new 2 Draft Copy | By DVD | 3rd Quarter |
| 2: TVC Production Previous 2 Final Copy | By DVD |  |
| 3: Broadcasting/Telecasting Execution plan and Execution report for last 4 months | By A4 size in Xcel Sheet and by Drop box |  |
| 1: New 2 TVC Draft Copy | By DVD | 4th Quarter |
| 2: Old 2 TVC Final copy | By DVD |  |
| 3: Telecasting plan | By A4 paper/ xcel sheet in dropbox |  |
| 4: Lottery and Loyalty program media coverage planning | By A4 paper/ xcel sheet in dropbox |  |
| 5: Last previous quarter execution report | By A4 paper/ xcel sheet in dropbox |  |
| 1: Old 2 TVC Final copy | By DVD | 5th Quarter |
| 2: Telecasting plan | By A4 paper/ xcel sheet in dropbox |  |
| 3: Lottery and Loyalty program media coverage planning | By A4 paper/ xcel sheet in dropbox |  |
| 4: Last previous quarter execution report | By A4 paper/ xcel sheet in dropbox |  |
| 1: Telecasting plan | By A4 paper/ xcel sheet in dropbox | 6th Quarter |
| 2: Lottery and Loyalty program media coverage planning | By A4 paper/ xcel sheet in dropbox |  |
| 3: Last previous quarter execution report | By A4 paper/ xcel sheet in dropbox |  |

- Completion Report

The draft reports to be submitted by the Consultant may contain any tentative conclusions arrived at by the Consultant. The PIU, NBR will make all efforts to provide comments within four weeks of receipt of draft reports.  The Final Report, reflecting the comments received, shall be prepared and submitted to the NBR within further two weeks period.  All media products need to be delivered in MP4 and AVI files through USB, hard disks and DVDs.

1: Six TVC Soft Copy in DVD

2: All media report

3: Monitoring report

- Indicative TRP report

This report should be accompanied with the completion report. It is expected that the firm/agency would be able to provide an indicative number of the total viewership of these TV products.

9. Services and Facilities Provided by the Client

Client will provide all necessary administrative support, access to relevant information and assistance in approaching public and private entities required for due performance of the services.

The Client will NOT provide the following:

(a) Office spaces and regular office furniture for the personnel of the Consultant.

(b) Computers, printers, photocopiers, fax machine, land telephones, office furniture and fixture and other office equipment

(c) Any residential accommodation for any staff of the Consultant in the premises of Client’s staff quarters.

(d) Any transport facility to any staff of the Consultant during the contract period.

10. Logistic and Financial Requirements of the Consulting firm for Contract:

- The firm/agency should have adequate and appropriate logistical facilities and human resources including expert/specialized to organize, implement, management, coordination, monitoring and reporting of such kind of campaign.

- The Firm/Agency should have proven prior experience to manage A grade  director, Videography Guy and Editor.

- The firm/agency should have at least 7 years of experience in Media Buying for TV.

- The firm/agency should have at least 7 years of experience in Media Planning for TV.

- Experience in airing TV programs would be an added advantage.

- The firm/agency must have the experience of working for at least two government projects.

- The firm/agency should be subscribed with all the TV Planning and Monitoring software available in the market.

- Ability to implement its proposed implementation plan within proposed time schedule & cost.

- Brochure/brief description of the Firm.

- Legally registered organization under the laws of Bangladesh.

- Trade license valid for 2015-16

- VAT registration certificate.

- Financial statement for the last Financial Year.

- List of major clients with contacts.

- Bank solvency certificate or credit facility of Taka 25 (Twenty Five) lac.

- CV of  all key professionals and

- Experience of related government work.

11. Institutional Arrangement

The Government of Bangladesh, through the MoF, is the Recipient for the credit of the Program/ Project. The Program is being implemented by the National Board of Revenue and the ERD. The ERD provide guidance to the implementing agency as the Program is implemented, and provide technical assistance and administrative support to resolve potential issues, including those related to the release of funds by the Ministry of Finance. The ERD is also responsible for reporting to IDA on the program results and DLIs.

A high level Program Steering Committee is responsible for ensuring high level drive and for managing critical issues that affects project implementation. The Committee consisting of ten members will be co-chaired by NBR’s Chairman, who is also the Secretary of the Internal Resource Division, with Member (VAT Policy) as the member-secretary of the Committee. The Committee meets at least quarterly to review the reform progress unless there is a need to convene immediate meetings. A Program Implementation Committee chaired by the NBR Board Member for VAT Enforcement and IT was also established. The Program Implementation Committee is responsible for overseeing program activities, monitoring procurement, and taking action as needed to ensure successful implementation of the program.

A Program Implementation Unit has been established by the NBR. It is headed by the Project Director, and it consists of three Deputy Project Directors, one accountant officer, office assistant-computer operator and supporting staff. The Project Director reports to the Program Steering Committee. The Unit is responsible for overseeing program implementation, and overall program coordination and management. The program is implemented in coordination with other initiatives funded by development partners and uses the pre-existing donor harmonization architecture.