GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH

Ministry of Finance/Internal Resources Division

National Board of Revenue

(NBR)

Term of References (TOR)

FOR

Selection of National Consulting Firm

For

Package SD15.2

Taxpayer Awareness Building Campaign-Talk Show

# Service Type: Talk Show Making, Live Talk show Planning, Business talk show, Media and broadcasting plan

Beneficiary Country: Government of the People’s Republic of Bangladesh

Contracting Authority: VAT Online Project (VOP), The National Board of Revenue (NBR)

- Background of the Project

The National Board of Revenue (NBR) has been allocated public funds from the Government of the People’s Republic of Bangladesh (GOB) (which has been provided funds to support this project through the World Bank’s Program for Results) towards the cost of “VAT and Supplementary Duty Act, 2012 (online) Implementation Project” and, intends to apply part of the proceeds with these funds for eligible payments to selected firms/agencies for delivering the services as per scope of the project.

To properly implement and effectively administer the new VAT law, the NBR, initiated its VAT Online Project (VOP). This new system will provide the best fit for the organization’s new business practices and processes. The VOP has been tasked with introducing a modern, user friendly and efficient VAT program through consultation, collaboration and co-design of the system.  The National Board of Revenue (NBR) has established Project Implementation Unit (PIU) under the VAT Online Project (VOP). The activities of the PIU will contribute towards increasing access to new VAT services and improve VAT law in Bangladesh. In order to reach these objectives, a nationwide inter-active multi-media campaign will be launched using audio, video, print and online media.  Against this backdrop, the NBR is seeking to appoint an eligible firm/agency to produce and disseminate television talk shows for increasing awareness among national taxpayers.

- Objectives of the assignment:

Key objectives of the NBR’s taxpayer awareness program are expected to influence, educate, change and enthuse taxpayers to comply with the new VAT law.  The awareness program is also expected to underpin the correction process for those who will not comply with the new law.

It should be noted that the success of this awareness and outreach program would be depended upon achieving the following specific communication sub-objectives, which the interested vendor must address in their production:

- Information dissemination about VAT, new VAT Law and VAT online project among public and the tax payers.

- Building trust between taxpayers and the Government by underlining transparency, positive and effective sides of the new VAT system.

- Constructing positive attitudes of the VAT Payers, VAT collectors and general public towards VAT.

2.a. Message Framing

Messages of these documentary products are required to be framed around four key themes that compliments above specific communication sub-objectives:

- Information and Education: Information and education refers to the dissemination and education of members of public including tax payers regarding what is VAT, the new online VAT system, new payment and accounting system, how the new law is different than the old law, how to register, who needs to be registered and why it is important to register.

- Encouragement and Awareness: Refers to encourage and aware VAT payers to register online, and enthuse them to adopt the new system.

- Advocacy and Influence: Here refers to turning VAT payers as advocates of the new law who would also influence peers towards welcoming the VAT online system. In this regard it is important that documentary productions would highlight the fact that the VAT payers and end consumers are contributing in building Bangladesh.

- Correction: Here refers to the implication for not complying with the law.

2.b.1. Primary Audience

- The Primary audience of this campaign is general public including the VAT payers (businessmen/ shop owners/corporations).

- Young generation.

- Influencer (including civil society members, celebrities and academia)

- Media as a multiplier

2.b.2. Secondary Audience

- NBR officials working across the country.

- Other Government agencies would be aware of this initiative.

3.  The Scope of Services (Including Production and Dissemination):

3.a. 1. TV Talk Shows: A total of 100 talk shows with a minimum duration of 25 minutes should be produced with an aim to meet three objectives and Four-message framing approaches mentioned above. That plan must include a balanced and rational distribution of talk shows between live talk show, recorded talks show and Specific business talk shows. TV show anchor or guest will be selected by PIU. Proposal should come from Agency/Service Firm. Communication consultants should follow-up the regular content and objectives.

3.a. 2 Broadcast Schedule: Spread over the contract period in leading private and government TV channels where spot/insertion should be 100. A detail media insertion plan is required to be submitted with the proposal with proper TRP. During the broadcast of these talk shows, the TV screens must broadcast selected TV scrolls (at least four in total) on VAT and the TV screens must be branded by the VAT online logo for few seconds. Length of logo branding during the broadcast of the program would be subject to agreement between the PIU and the service provider. Broadcast Schedule is also flexible for any other extra TVC, TV Documentary and Lottery Live Show etc. from NBR as per need.

(Proprietary Rights of all final production materials will be retained by the NBR)

3. Table 1. Indicative Required Key Professionals:

| Designation | Qualification | Experience |
| --- | --- | --- |
| Director for Video production (1X12 person months intermittently spread over the contract period) | University degree (Minimum Bachelor’s degree) | Minimum 7 years of experience in directing and managing TV talk show /Business and political Talk show productions Previous experience of working with the government would be a plus. Otherwise a very vast knowledge about Tax Payer and Government issues. Very positive about new VAT Law. Understand and aware of new VAT Law issues. |
| Production manager (1X 12 Person months intermittently spread over the contract period) | University degree (Minimum Bachelor’s degree) | At least five years of experience in relation to production and management. |
| Media Marketing Manager (1X12 months intermittently spread over the contract period | University Degree (Minimum Bachelor’s Degree) | Proven experience of buying media chunks Previous experience of working in a government project would be a plus. |
| Research and Development Management Officer | University Degree (Minimum Bachelor Degree) | Proven Experience of research on law and Taxpayer issues; Positive about new VAT Law; Very Good analytical power on law and TAX payers |

3. Table 2. Required Indicative Other Professionals

None

3.b. Period of Performance

Expected contract period is July 2017 to December 2018.

4.a. Deliverables:

100 Talk shows in appropriate media format alongside of following detailed reports comprising when and where those talk shows and scrolls were broadcasted.  Indicative detail contents of each report are written below.

- Table 1:

| SL No | Milestone & Deliverables | Content & Number of Copies | Schedule |
| --- | --- | --- | --- |
| 1 | Inception Report- Work Plan | 1 Paper and 4 electronic Copies | Within 30 days of the inception of the work |
| 2 | Quarterly Progress Report | 1 Paper and 4 electronic Copies | In every three months from the inception of the work (At least Six). |
| 3 | Completion Report (all requested deliverable ) of the Taxpayer Advertising Campaign | 1 Paper and 4 electronic Copies | Within a month of the completion of the project |
| 4 | Indicative TRP report | 1 Paper and 4 electronic copies | Within a month of the completion of the project |
| 5 | Contents of media products in DVDs and USBs | 10 copies | With completion report (10) |

- The consulting firm/agency will prepare plans including names of the guests of the aforementioned broadcast materials after obtaining the approval of the relevant NBR authority.

- Agency or firm will provide minimum 3(Three) CV of each key professional as per their availability.

- All contents produced for this project needs to be delivered in MP4 and AVI format in pen drives.

- The consulting firm should prepare reports (see the schedule of reports below), describing plan, progress and completion of the assignment. These reports should provide a clear presentation and include a table of contents and an executive summary.

- All paragraphs in the executive summary, the text, and the Annexure, shall be numbered to facilitate communication on the contents of reports.

- All reports shall be accompanied with a PDF soft copy on a CD (1 Master and 3 additional copies shall be included)

4.b. Content of Reports

Following reports are required to submit to PIU, Dhaka:

- Inception Report – Work Plan (Draft and Final)

Within the ten days of selection of the contract, the consulting firms must provide a draft inception report which will include a detailed work plan which shall contain the final detailed time-task-schedule charts listing all the tasks, estimate by task of both the staff time input by the consulting firms and counterpart personnel and the time requirement for task completion in bar chart format and also include supporting text describing the bases of the program.  The PIU, NBR will make all efforts to furnish comments on the Inception Report -Work Plan within a week of the reception of the draft inception plan.

N:B: Plan should be very details as much as possible. PIU have the authority to change the plan any time.

- Quarterly Progress Report

Quarterly Progress Report must include, among others, content of the report, photographs of each activity completed in each quarter and a list of media content under production/ are produced. If those contents are disseminated through media outlets, the report must ensure it features a list of outlets through which those media contents were disseminated including the time of the dissemination. Soft copies of finished products in the case of completion of production at the time of the submission of respective quarterly progress reports must be accompanied with the report.  The total number of quarterly progress report must be at least six but depending upon the campaign roll out plan, procedure and implementation, the number of progress report delivery could be enhanced. If the PIU advised so the firm/agency must comply with that demand.

4.Table. 2:

| Name of Contents | Progress Report | Time Schedule |
| --- | --- | --- |
| 1: All talk show video | By DVD | 1st Quarter |
| 2: Broad-casting Time and Monitoring report | By A4 Paper & Dropbox |  |
| 3: Plan for next quarter | By A4 Paper & Dropbox Xcel Sheet |  |
| 1: All talk show video | By DVD | 2nd Quarter |
| 2: Broad-casting Time and Monitoring report | By A4 Paper & Dropbox |  |
| 3: Plan for next quarter or any other advise | By A4 Paper & Dropbox Xcel Sheet |  |
| 1: All talk show video | By DVD | 3rd Quarter |
| 2: Broad-casting Time and Monitoring report | By A4 Paper & Dropbox |  |
| 3: Plan for next quarter or any other advise | By A4 Paper & Dropbox Xcel Sheet |  |
| 1: All talk show video | By DVD | 4th Quarter |
| 2: Broad-casting Time and Monitoring report | By A4 Paper & Dropbox |  |
| 3: Plan for next quarter or any other advise | By A4 Paper & Dropbox Xcel Sheet |  |
| 1: All talk show video | By DVD | 5th Quarter |
| 2: Broad-casting Time and Monitoring report | By A4 Paper & Dropbox |  |
| 3: Plan for next quarter or any other advise | By A4 Paper & Dropbox Xcel Sheet |  |
| 1: All talk show video | By DVD | 6th Quarter |
| 2: Broad-casting Time and Monitoring report | By A4 Paper & Dropbox |  |
| 3: Plan for next quarter or any other advise | By A4 Paper & Dropbox Xcel Sheet |  |

- Completion Report

The draft reports to be submitted by the Consultant may contain any tentative conclusions arrived at by the Consultant. The PIU, NBR will make all efforts to provide comments within four weeks of receipt of draft reports.  The Final Report, reflecting the comments received, shall be prepared and submitted to the NBR within further two weeks period.  All media products need to be delivered in MP4 and AVI files through USB, hard disks and DVDs.

- Indicative TRP report

This report should be accompanied with the completion report. It is expected that the firm/agency would be able to provide an indicative number of the total viewership of these TV products.

5. Services and Facilities Provided by the Client

Client will provide all necessary administrative support, access to relevant information and assistance in approaching public and priVATe entities required for due performance of the services.

The Client will NOT provide the following:

(a) Office spaces and regular office furniture for the personnel of the Consultant.

(b) Computers, printers, photocopiers, fax machine, land telephones, office furniture and fixture and other office equipment.

(c) Any residential accommodation for any staff of the Consultant in the premises of Client’s staff quarters.

(d) Any transport facility to any staff of the Consultant during the contract period.

5.a. Logistic and Financial Requirements of the Consulting farm for Contract:

- The firm/agency should have adequate and appropriate logistical facilities and human resources including expert/specialized to organize, implement, management, coordination, monitoring and reporting of such kind of campaign.

- The firm/agency should have at least 7 years of experience in Media Buying for TV.

- The firm/agency should have at least 7 years of experience in Media Planning for TV.

- Experience in airing TV programs would be an added advantage.

- The firm/agency must have the experience of working for at least two government projects.

- The firm/agency should be subscribed with all the TV Planning and Monitoring software available in the market.

- Ability to implement its proposed implementation plan within proposed time schedule & cost.

- Brochure/brief description of the Firm.

- Legally registered organization under the laws of Bangladesh.

- Trade license valid for 2015-16

- VAT registration certificate.

- Financial statement for the last Financial Year.

- List of major clients with contacts.

- Bank solvency certificate or credit facility of Taka 25 (Twenty Five) lac.

- CV of key professionals and

- Experience of related government work.

6. Institutional Arrangement

The Government of Bangladesh, through the MoF, is the Recipient for the credit of the Program/ Project. The Program is being implemented by the National Board of Revenue and the ERD. The ERD provide guidance to the implementing agency as the Program is implemented, and provide technical assistance and administrative support to resolve potential issues, including those related to the release of funds by the Ministry of Finance. The ERD is also responsible for reporting to IDA on the program results and DLIs.

A high level Program Steering Committee is responsible for ensuring high level drive and for managing critical issues that affects project implementation. The Committee consisting of ten members will be co-chaired by NBR’s Chairman, who is also the Secretary of the Internal Resource Division, with Member (VAT Policy) as the member-secretary of the Committee. The Committee meets at least quarterly to review the reform progress unless there is a need to convene immediate meetings. A Program Implementation Committee chaired by the NBR Board Member for VAT Enforcement and IT was also established. The Program Implementation Committee is responsible for overseeing program activities, monitoring procurement, and taking action as needed to ensure successful implementation of the program.

A Program Implementation Unit has been established by the NBR. It is headed by the Project Director, and it consists of three Deputy Project Directors, one accountant officer, office assistant-computer operator and supporting staff. The Project Director reports to the Program Steering Committee. The Unit is responsible for overseeing program implementation, and overall program coordination and management. The program is implemented in coordination with other initiatives funded by development partners and uses the pre-existing donor harmonization architecture.